## Sheet1
Feature | User Story | Story Points | Sprint | Subtasks
Homepage for Agile Manifesto | Design and implement a visually appealing homepage. | 3 | Sprint 1 | Create wireframes; Develop layout; Integrate animations; Test homepage.
Homepage for Agile Manifesto | Add an introduction to Agile and its history. | 2 | Sprint 1 | Research Agile history; Write content; Add to homepage.
Homepage for Agile Manifesto | Include navigation to other sections of the platform. | 2 | Sprint 1 | Design navigation; Implement links; Test navigation.
Agile Values and Principles | Create a page to display the four core Agile Values. | 3 | Sprint 2 | Design layout; Add Agile values; Test display.
Agile Values and Principles | Implement an interactive feature to explain the 12 principles. | 5 | Sprint 2 | Create interactive elements; Add hover effects; Test interactions.
Agile Values and Principles | Add examples to illustrate each value and principle. | 5 | Sprint 2 | Research examples; Add examples; Test examples.
Resource Library | Design a library for Agile practices(Scrum, Kanban, etc.) | 5 | Sprint 3 | Design resource layout; Add categories; Test resource display.
Resource Library | Include downloadable resources like templates and guides. | 3 | Sprint 3 | Gather templates; Upload resources; Test downloads.
Resource Library | Add search and filter functionality. | 8 | Sprint 3 | Develop search functionality; Add filters; Test search and filter.
Collaboration Features | Develop a discussion forum for users. | 8 | Sprint 4 | Design forum UI; Develop backend APIs; Integrate frontend; Test forum.
Collaboration Features | Enable users to comment on resources and principles. | 5 | Sprint 4 | Design comment UI; Develop comment API; Integrate API; Test comments.
Collaboration Features | Implement user authentication for collaboration features. | 8 | Sprint 4 | Develop authentication API; Implement login/logout; Test authentication.